## Instructions
Lifecycle Gates, Staged Implementation, and Dossier Status
Resource ID | AIHE-D02
Primary chapter | 12 — Decision Architecture and Lifecycle Governance
Additional alignment | 4, 9, 11, 12
Version | V1.0
Purpose | Control increasing commitment through problem, readiness, evidence, local validation, economics, pilot, scale, renewal, and retirement gates.
Instructions | Create a governed copy; complete the record with the responsible multidisciplinary team; distinguish evidence from assumptions; preserve versions, owners, review triggers, and exit criteria.
Data protection | Do not enter identifiable patient information, credentials, private keys, or confidential contract details into uncontrolled copies.
Status | Decision-support and documentation resource; not a validated clinical, legal, regulatory, procurement, accreditation, cybersecurity, or health technology assessment instrument.

## Blank Template
Gate or stage | Required evidence and output | Status | Condition, remediation, or exit | Owner, decision, and date
Problem and comparator | Baseline burden, alternatives, intended action, outcomes, and opportunity cost
Readiness and data | Infrastructure, data fitness, workflow, workforce, quality, governance, and capacity
External evidence and due diligence | Exact version, applicability, independent appraisal, limitations, and claim challenge
Local silent validation | Technical and human–AI performance, subgroups, workflow, safety, and monitoring feasibility
Economic and affordability review | Lifecycle cost, pricing, outcomes, budget impact, uncertainty, and benefit realization
Controlled pilot | Training, fallback, incident process, measures, thresholds, duration, and decision criteria
Conditional scale | Transfer conditions, implementation strategies, governance capacity, contract, and portfolio effects
Renewal or retirement | Current comparator, evidence, value, safeguards, material changes, alternatives, and exit

## Worked Example
Gate or stage | Required evidence and output | Status | Condition, remediation, or exit | Owner, decision, and date
Problem and comparator | Baseline burden, alternatives, intended action, outcomes, and opportunity cost | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Clinical service lead
Readiness and data | Infrastructure, data fitness, workflow, workforce, quality, governance, and capacity | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Quality lead
External evidence and due diligence | Exact version, applicability, independent appraisal, limitations, and claim challenge | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Data steward
Local silent validation | Technical and human–AI performance, subgroups, workflow, safety, and monitoring feasibility | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Health economist
Economic and affordability review | Lifecycle cost, pricing, outcomes, budget impact, uncertainty, and benefit realization | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Procurement lead
Controlled pilot | Training, fallback, incident process, measures, thresholds, duration, and decision criteria | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Clinical service lead
Conditional scale | Transfer conditions, implementation strategies, governance capacity, contract, and portfolio effects | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Quality lead
Renewal or retirement | Current comparator, evidence, value, safeguards, material changes, alternatives, and exit | Conditionally ready | Proceed conditionally after documented remediation, owner approval, and verification. | Data steward