# AIHE-EX12 — Incident Corrective Action and Reconstruction Log

Current digital location: Resource Set D — Procurement, Implementation, and Lifecycle Governance. Stable resource ID retained for continuity across companion editions.

Synthetic worked example

| Current digital location | Resource Set D — Procurement, Implementation, and Lifecycle Governance |
| --- | --- |
| Related book chapters | Chapter 5: Quality, Accreditation, and Organizational Learning; Chapter 10: Governance, Accountability, and Institutional Risk; Chapter 10: Governance, Accountability, and Institutional Risk; Chapter 12: Decision Architecture and Lifecycle Governance; Chapter 12: Decision Architecture and Lifecycle Governance |
| Workflow step | 08: 08_Monitoring_Lifecycle |
| Version | 6.0.0 ¦ aligned to the fifteen-chapter reference edition and Resource Sets A–E |

Purpose. Classify and reconstruct technical, clinical, workflow, privacy, cybersecurity, equity, and communication incidents.

Use note. Use the resource as a versioned institutional record. Adapt it to local law, policy, clinical practice, information security, procurement, and health-technology-assessment requirements. Do not enter identifiable patient data or confidential credentials into public copies.

Worked-example status. All names, organizations, figures, findings, and decisions are fictional and are included only to demonstrate completion logic.

# How to use this resource

A material incident is not closed merely because service resumes. Closure requires reconstruction, accountable corrective action, evidence of effectiveness, and explicit recording of residual uncertainty.

# Incident reconstruction

| Field | Minimum required content | Incident-specific record |
| --- | --- | --- |
| Identification | Incident ID, date/time, reporter, system, version, site, intended use. | INC-2026-014; ambient documentation v3.4; cardiology clinic. |
| Categories | Primary and secondary categories from the seven-category taxonomy. | Primary: communication; secondary: workflow. |
| Affected scope | Patients, staff, records, pathway, duration, and scale. | Seven draft notes; no signed record affected. |
| Data and provenance | Source, time, transformations, missingness, quality, and changes. | Transcript segment duplicated after reconnect. |
| Model and configuration | Model/software, thresholds, prompts, retrieval, interfaces, connected sources. | Model 3.4; prompt 11; no retrieval. |
| AI output | Score, recommendation, generated content, uncertainty, alert, or action. | Duplicated medication instruction in draft note. |
| Human action and rationale | Recipient, information, accept/reject/modify/ignore/escalate and rationale. | Clinician corrected before signing and reported pattern. |
| Clinical and operational context | Workload, timing, staffing, patient condition, capacity, downtime, workarounds. | Network reconnect during high-volume clinic. |
| Immediate response | Protection, containment, restriction, rollback, notification, fallback. | Template disabled; manual documentation activated. |
| Cause and contributing factors | Technical, human, workflow, governance, vendor, communication causes and uncertainty. | Reconnect bug plus absent duplicate-content check. |
| Corrective and preventive action | Owner, remediation, revalidation, monitoring, training, contract action, deadline. | Vendor patch; duplicate detector; user notice; 30-day review. |
| Closure | Effectiveness evidence, affected records addressed, residual risk, authority, date. | Conditional closure after 30 days with no recurrence. |

# Incident-category review

| Category | Involvement | Finding | Owner and action |
| --- | --- | --- | --- |
| Technical | Secondary | Reconnect duplication defect. | Vendor patch and local regression test. |
| Clinical | Potential | Content could cause harm if signed. | Clinical safety sampling. |
| Workflow | Secondary | High-volume reconnect and review burden. | Revise downtime/reconnect workflow. |
| Privacy | Not involved | No unauthorized disclosure. | Document finding. |
| Cybersecurity | Not involved | No malicious activity identified. | Security sign-off. |
| Equity | Not established | No subgroup pattern; sample small. | Monitor recurrence by service and language. |
| Communication | Primary | Generated instruction was inaccurate and repetitive. | Template control and clinician notification. |

# Decision and review record

| Field | Guidance | Record |
| --- | --- | --- |
| Recommended status | Proceed / proceed with conditions / redesign / restrict / pause / replace / retire | Proceed with conditions |
| Mandatory safeguards | Safety, lawful data use, privacy/security, equity, human oversight, monitoring, ability to stop | Passed with two conditions |
| Material unresolved issues | Record gaps that could change the decision | Local subgroup sample remains small |
| Conditions, owners, and due dates | Link every condition to an accountable owner and verification date | Clinical safety lead—complete 90-day review |
| Decision authority and date | Named committee or executive authority | AI Governance Committee; 30 July 2026 |
| Next review or trigger event | Date and event-triggered review conditions | Monthly during pilot; immediate review after material update |