# AIHE-EX11 — Material Change and Renewal Review

Current digital location: Resource Set D — Procurement, Implementation, and Lifecycle Governance. Stable resource ID retained for continuity across companion editions.

Synthetic worked example

| Current digital location | Resource Set D — Procurement, Implementation, and Lifecycle Governance |
| --- | --- |
| Related book chapters | Chapter 9: Problem-First Procurement and Vendor Governance; Chapter 12: Decision Architecture and Lifecycle Governance; Chapter 12: Decision Architecture and Lifecycle Governance |
| Workflow step | 08: 08_Monitoring_Lifecycle |
| Version | 6.0.0 ¦ aligned to the fifteen-chapter reference edition and Resource Sets A–E |

Purpose. Assess model, data, interface, workflow, vendor, contract, policy, performance, risk, and annual renewal changes.

Use note. Use the resource as a versioned institutional record. Adapt it to local law, policy, clinical practice, information security, procurement, and health-technology-assessment requirements. Do not enter identifiable patient data or confidential credentials into public copies.

Worked-example status. All names, organizations, figures, findings, and decisions are fictional and are included only to demonstrate completion logic.

# How to use this resource

A material change is any change that may alter intended use, evidence applicability, performance, risk, workflow, economics, obligations, or the ability to monitor and stop. Renewal is an evidence-based lifecycle decision, not an automatic contract event.

# Material-change review

| Change domain | Finding or description | Required evidence and assessment | Owner / due | Decision |
| --- | --- | --- | --- | --- |
| Intended or excluded use | Vendor proposes automated follow-up suggestions. | New intended-use statement, clinical/economic analysis, human oversight, downstream-utilization plan. | Clinical sponsor / 30 days | Do not activate. |
| Population, site, or users | Expansion from two clinics to all specialties. | Transportability, workflow, training, capacity, subgroup, and budget assessment. | Program lead / 45 days | Pilot selected sites. |
| Model, version, or threshold | Version 4.2 replaces 4.1. | Release evidence, local regression tests, calibration, safety, rollback. | Validation lead / 14 days | Conditional acceptance. |
| Training, retrieval, or reference data | Knowledge base updated. | Provenance, scope, update date, conflict testing, red-team results. | Content owner / 14 days | Approve after testing. |
| Input, interface, coding, terminology | FHIR interface profile changes. | Mapping and conformance tests, data-quality and latency review. | Data steward / 14 days | Remediate and repeat. |
| Workflow, oversight, or capacity | Review moves from physician to nurse. | Role, competency, authority, burden, escalation, safety, equity. | Service lead / 30 days | Redesign. |
| Vendor, subcontractor, hosting, or security | New model hosting subcontractor. | Security, location, data flow, contract, incident, continuity review. | Security/contract / 30 days | No transfer before approval. |
| Pricing, support, or service level | Variable fee increases 8%. | Volume scenarios, cap, benefit realization, alternatives, negotiation. | Procurement / renewal | Renegotiate. |
| Law, standard, or policy | New local AI policy takes effect. | Gap analysis, impact, remediation, evidence and approval. | Governance / 60 days | Conditional continuation. |
| Observed performance, equity, safety, or value | Correction time exceeds expected value. | Root-cause analysis, threshold, workflow, cost, benefit, restriction options. | Service/finance / 30 days | Restrict pending action. |

# Annual renewal review

| Review element | Required record |
| --- | --- |
| Current scope | Intended use, excluded uses, version, population, sites, users, and accountable owner. |
| Accumulated evidence | External updates, local validation, real-world performance, incidents, human factors, subgroups. |
| Realized value and burden | Benefits, workload, lifecycle cost, budget, downstream utilization, environmental and public value. |
| Residual risk | Open incidents, uncertainty, privacy, cybersecurity, equity, communication, continuity. |
| Regulatory and standards alignment | Applicable law, policy, standards, management-system and assurance changes. |
| Vendor and contract | Service levels, updates, audit, support, pricing, subcontractors, data rights, exit. |
| Monitoring and fallback | Data access, metrics, thresholds, owners, fallback, pause, rollback, de-adoption readiness. |
| Alternatives and opportunity cost | Current comparators, internal build, other vendor, process redesign, staffing, retirement. |
| Renewal decision | Renew, renew with conditions, renegotiate, restrict, replace, or retire. |
| Authority and next review | Decision authority, dissent, conditions, owners, dates, trigger events. |

# Decision and review record

| Field | Guidance | Record |
| --- | --- | --- |
| Recommended status | Proceed / proceed with conditions / redesign / restrict / pause / replace / retire | Proceed with conditions |
| Mandatory safeguards | Safety, lawful data use, privacy/security, equity, human oversight, monitoring, ability to stop | Passed with two conditions |
| Material unresolved issues | Record gaps that could change the decision | Local subgroup sample remains small |
| Conditions, owners, and due dates | Link every condition to an accountable owner and verification date | Clinical safety lead—complete 90-day review |
| Decision authority and date | Named committee or executive authority | AI Governance Committee; 30 July 2026 |
| Next review or trigger event | Date and event-triggered review conditions | Monthly during pilot; immediate review after material update |