# AIHE-EX16 — Reproducible Analysis, Model Risk, and Code Quality Checklist

Current digital location: Resource Set B — Economic Evaluation, Evidence, and Decision Modeling. Stable resource ID retained for continuity across companion editions.

Synthetic worked example

| Current digital location | Resource Set B — Economic Evaluation, Evidence, and Decision Modeling |
| --- | --- |
| Related book chapters | Chapter 12: Decision Architecture and Lifecycle Governance; Chapter 8: Decision Modelling and Simulation Under Uncertainty; Chapter 11: Evidence, Validation, and Real-World Evaluation; Computational instruments in the Digital Resource Companion; principally Chapters 8, 11, and 12 |
| Workflow step | 03: 03_Evidence_Validation |
| Version | 6.0.0 ¦ aligned to the fifteen-chapter reference edition and Resource Sets A–E |

Purpose. Verify data provenance, environments, versioning, testing, validation, uncertainty, security, release, and archive controls.

Use note. Use the resource as a versioned institutional record. Adapt it to local law, policy, clinical practice, information security, procurement, and health-technology-assessment requirements. Do not enter identifiable patient data or confidential credentials into public copies.

Worked-example status. All names, organizations, figures, findings, and decisions are fictional and are included only to demonstrate completion logic.

# How to use this resource

Use this checklist before an analysis, spreadsheet, model, dashboard, or code package is relied upon for a material decision or public release.

# Reproducibility and model-risk checklist

| Domain | Minimum requirement | Status | Evidence / result | Owner and action |
| --- | --- | --- | --- | --- |
| Decision specification | Versioned population, comparator, perspective, horizon, outcomes, and decision rule. | Pass | Specification v1.3 approved. | Health economist |
| Data provenance | Sources, access, schema, transformations, exclusions, and lineage. | Conditional | Lineage complete; one terminology map pending. | Data steward—close before pilot |
| Environment | Language, packages, operating environment, dependency lock, and hardware assumptions. | Pass | Python 3.11 environment lock archived. | Analytics lead |
| Version control | Code, schema, configuration, model, documentation, and outputs have versions. | Pass | Tagged release and immutable output folder. | Analytics lead |
| Code review and testing | Independent review, automated tests, edge cases, and failure handling. | Conditional | Unit tests pass; external review scheduled. | Independent reviewer |
| Randomness and convergence | Seeds, replications, warm-up, run length, convergence, and tolerance. | Pass | Seed, 2,000 replications, convergence trace. | Modeler |
| Verification and validation | Conceptual model, equations, code, face validity, comparison, and extreme tests. | Pass | Review record and extreme-case results. | Model-validation lead |
| Uncertainty and sensitivity | Parameter, structural, implementation, and scenario uncertainty. | Pass | PSA and structural scenarios included. | Health economist |
| Privacy and security | Secrets, identifiers, access, logs, third-party code, vulnerabilities, and disclosure. | Pass | Synthetic data only; dependency scan complete. | Security lead |
| Output traceability | Outputs regenerate from archived inputs and code. | Pass | Re-run hash matches release output. | Analytics lead |
| Release and archive | Approver, limits, licenses, archive, continuity, and next review. | Conditional | Release approval pending two actions. | Program owner |

# Release decision

| Field | Record |
| --- | --- |
| Release class | Governed pilot analysis; not for autonomous clinical use. |
| Open conditions | Terminology map and independent code review. |
| Approval authority | Director, Health Analytics and AI Governance Committee. |
| Archive location | Controlled repository release 2.0.0. |
| Next review | Before any data, model, workflow, or intended-use change. |

# Decision and review record

| Field | Guidance | Record |
| --- | --- | --- |
| Recommended status | Proceed / proceed with conditions / redesign / restrict / pause / replace / retire | Proceed with conditions |
| Mandatory safeguards | Safety, lawful data use, privacy/security, equity, human oversight, monitoring, ability to stop | Passed with two conditions |
| Material unresolved issues | Record gaps that could change the decision | Local subgroup sample remains small |
| Conditions, owners, and due dates | Link every condition to an accountable owner and verification date | Clinical safety lead—complete 90-day review |
| Decision authority and date | Named committee or executive authority | AI Governance Committee; 30 July 2026 |
| Next review or trigger event | Date and event-triggered review conditions | Monthly during pilot; immediate review after material update |